## Sheet1
ID | As a/an | I want to | so that | notes | priority | status | Date Requested | Date Accomplished
1 | user | Enter Student Numbers using a textbox | The student numbers enter the database |  | High | Done | 2018-02-06 | 2018-02-10
2 | user | View the time-ins of today | I view the time-ins of that day |  | Normal | Done | 2018-02-06 | 2018-02-10
3 | user | View the current student numbers timed-in | I can keep track of the current time-ins |  | High | Done | 2018-02-06 | 2018-02-13
4 | user | To be able to use a barcode scanner | My job will be easier | Simulate using Android barcode Scanner | High | Done | 2018-02-06 | 2018-02-13
5 | user | To be able to generate report from data | I can see the trends in the data provided |  | Normal | Done | 2018-02-06 | 2018-03-22
5.1 | user | To be able to generate report from data per hour, day, week, month, year | I can see the trends in the data provided |  | Normal | Done | 2018-02-06 | 2018-02-16
5.2 | user | To be able to generate report from data in a specific timespan | I can see the trends in the data provided |  | Normal | Done | 2018-02-06 | 2018-02-16
5.3 | user | To be able to generate report from data per degree program | I can see the trends in the data provided |  | Normal | Done | 2018-02-06 | 2018-02-16
5.4 | user | To be able to generate report from data per college | I can see the trends in the data provided |  | Normal | Done | 2018-02-06 | 2018-03-21
5.5 | user | To be able view peak hours and lean hours | I can see the trends in the data provided |  | Normal | Done | 2018-02-06 | 2018-03-22
6 | user | View a student's time in history | I can see the activity of a student |  | Normal | Done | 2018-02-08 | 2018-02-18
7 | user | View the remaining hours of a student | I can keep track of the student's remaining hours |  | High | Done | 2018-02-08 | 2018-02-18
8 | user | have a page/table for paid services | I can view payments made by users |  | Normal | Done | 2018-02-08 | 2018-03-09
After prototype 1 visit
9 | user | to be able to input a student number without the dash | users who enter the student numbers manually can omit the dash |  | low | Done | 2018-02-20 | 2018-03-10
10 | user | See the name of the students in the reports | I can view their names in the reports |  | High | Done | 2018-02-20 | 2018-02-20
11 | user | have different tabs for each type of time in | I can easily distinguish the different kinds of time ins |  | High | Done | 2018-02-20 | 2018-02-20
12 | user | to be able to view the paid services | I can keep track of the payments of students |  | Normal | Done | 2018-02-20 | 2018-03-12
13 | user | be able to see if a student has 1 hour left | I can be notified if the student has 1 hour left |  | Low | Done | 2018-02-20 | 2018-03-11
14 | user | be able to undo the time out | If I make a false time out I can easily revert |  | High | Unachievable | 2018-02-20
14* | user | to be able to have a checkbox for confirm timeout | I am able to confirm if the time out is correct |  | High | Done | 2018-03-17 | 2018-03-19
15 | user | be able to change the tag of the computer usage | If a student wants to change computer I can easily change their tag |  | Normal | Done | 2018-02-20 | 2018-03-17
After prototype 2 visit
16 | user | to have one merged input field for entering the student numbers | so that I will not be confused in entering the student number |  | High | Done | 2018-03-23 | 2018-04-09
17 | user | have a setting to charge time when using computers | so that I can change the setting in this field |  | Normal | Done | 2018-03-23 | 2018-04-19
17.1 | user | have an option of enabling time out confirmation | I have the settings centralised and remember |  | Normal | Done | 2018-03-23 | 2018-04-19
17.2 | user | have an option of enabling charged computer usage | I can enable/disable charged computer usage |  | Normal | Done | 2018-03-23 | 2018-04-19
18 | user | to be reminded to delete transactions after a year passes | so that the system will not slow down |  | High | Done | 2018-03-23 | 2018-04-09
18.1 | user | to generate reports within a year's interval | so that I can keep the data |  | High | Done | 2018-03-23 | 2018-04-09
18.2 | user | to delete the transactions after printing a year's interval | so that the system will not slow down |  | High | Done | 2018-03-23 | 2018-04-09
19 | user | to have another table for outsiders | so that I can keep track of outsider's paid transactions |  | Normal | done | 2018-03-23 | 2018-04-19
20 | user | to view numerical months as worded month | so that I can easily distinguish easily view months |  | Low | Done | 2018-03-23 | 2018-04-11
20.1 | user | to view numerical months as worded month in time-in tables | so that I can easily distinguish easily view months |  | Low | Done | 2018-03-23 | 2018-04-11
20.2 | user | to view numerical months as worded month in report generations | so that I can easily distinguish easily view months |  | Low | Done | 2018-03-23 | 2018-04-11
After prototype 3 visit
21 | user | to show drop-down calendar while selecting date | so that I can select date with ease |  | Low | Ongoing | 2018-04-20
22 | user | to add occupation options for visitor (e.g. Faculty, Researcher, etc.) | I can verify if the customer is a UP employee or not |  | Normal | Ongoing | 2018-04-20
23 | user | Official receipts must be input in correct format | it can be confirmed that it came from the UP Cashier |  | Normal | Ongoing | 2018-04-20
24 | user | admin privileges in accessing students and reports | transaction info will be remained classified |  | High | Ongoing | 2018-04-20
25 | user | to display tag number on time-out prompt | I can be verified who to notify |  | Low | Ongoing | 2018-04-20
26 | user | to notify if student or visitor has one hour left (Computer/ Charging) | I can notify the student and ask if he/she wishes for time extension |  | Normal | Ongoing | 2018-04-20
27.1 | user | additional filtering options on report (by usage) | I can have more report format options |  | Normal | Ongoing | 2018-04-20
27.2 | user | to generate sum of total transactions, separate students and visitors | I can give more detailed financial statements |  | High | Ongoing | 2018-04-20
28 | user | check box when deleting student | I have further confirmation for deleting the student's info |  | Low | Ongoing | 2018-04-20
Library Service Usage
C. M. Quibada, I. F. Narciso, C. C. Acoba, K. Floresca